## Slide 1
A COLLABORATION
A community engagement strategy for Altadena rebuild
Altadena Village · CoLab · Alting · Altagether
PRESENTED TO CAPS · MAY 21, 2026

## Slide 2
WHY WE'RE HERE
Altadena's commercial and public spaces are being rebuilt. There's no process for the community to shape what they become and see the impact of their input.
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 3
WHY WE'RE HERE
Separate schedules, no coordination
2026
2027
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
CIP
LA County Public Works
Survey
Comment period TBD
Regional Planning
WSGVAP refresh
Refresh cycle TBD
Sanitation
LA County sewer
Ongoing rebuild interaction
Water utilities
Las Flores · Lincoln · Rubio Cañon
Ongoing restoration & planning
Flood Control
LA County stormwater
Stormwater windows TBD
Edison / SCE
Undergrounding & restoration — ongoing
SoCalGas
Gas restoration ongoing
PUSD
School-site rebuild
Decisions TBD
Parks & Rec
LA County multi-benefit
Parks & green corridors TBD
Tree restoration
LA County · TreePeople · Altadena Bloom
Urban canopy restoration TBD
Commercial developers
Various private projects
Active rebuild projects ongoing
New permits & projects TBD
Paradigm
Edison's outreach consultant
Engagement windows TBD
Toole
LA County's planning consultant
Master plan in progress
No engagement scheduled
AND THE PFA
The Public Financing Authority has convened — but hasn't held the meetings required by its own bylaws. The engagement standard adopted at those meetings will be the default for every project above.
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 4
WHAT'S MISSING
Five gaps — and the values that close them
01
Local insight
Residents carry context the County doesn't have, with no channel for it to land.
02
Local agency
Commercial owners have coordinated a shared vision, but no defined path to the County's infrastructure rollout.
03
Coordination
Agencies plan in parallel, on separate schedules, with no shared way to coordinate.
04
Accountability
No way to track whether community input shaped what actually gets built.
05
Trauma-informed
No engagement design built for a community that's been through this much.
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 5
WHAT WE'RE PROPOSING
Five steps — content flows down, consensus flows up
↓
↓
↓ CONTENT FLOWS DOWN
01
Definition
Sponsors define their decision based on community standards — problem, ask, geographic area, timeline, and multi-modal delivery (text · video · Spanish · walking tours) with expert access.
WHO County agencies · utilities · developers · consultants
02
Training & Distribution
Through existing channels — Altagether's 150+ block captains and the commercial-owner network, trained to facilitate with on-call backup.
WHO Altagether captains · commercial-owner network · CoLab (training)
↑
↑
↑ CONSENSUS FLOWS UP
05
Shared record
The record goes public — tracked on a dashboard, visible to all stakeholders.
WHO All stakeholders see · working group maintains
04
Aggregation
Block deliberations compile into a coherent record — organized by area, corridor, zone, and by the sponsor's own categories. Private dialogue stays private; outcomes become public.
WHO Captains record · CoLab captures · Alting synthesizes
•
•
DELIBERATION
03
Facilitating Discussion
Block captains facilitate time-bound community deliberation at the block level.
WHO Block captains lead · Altadena public participates · local facilitators support
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 6
WORKED EXAMPLE
Fair Oaks Corridor (Immediate need)
↓
↓
↓ CONTENT FLOWS DOWN
01
Definition
CIP surveys customized for Altadena — by area, across six categories (Mobility · Stormwater · Sewer · Water · Energy · Multi-Benefit). Plain-language briefs in EN + ES.
02
Training & Distribution
Altagether's 150+ captains + commercial-owner network + QR signage at storefronts and yards.
↑
↑
↑ CONSENSUS FLOWS UP
05
Shared record
Structured packets to CIP — manually plotted on map. No automated dashboard yet.
04
Aggregation
Decision-record cards · shared Google docs · per-category compilation. Manual — no dashboard yet.
•
•
DELIBERATION
03
Facilitating Discussion
Walking tours · Zoom calls · facilitated input sessions · Design Fair for commercial owners and adjacent residents.
Fair Oaks is the hand-hacked version — the framework works while we build the automated tools (real-time dashboard, auto-aggregation) once funded.
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 7
PROJECT PLAN
What happens after endorsement
2026
2027
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
CAPS presentation
Today
May 21
ATC + Altagether ratification
Jun–Jul
EIFD advocacy
At PFA hearings
Funding push
Framework + toolkit build
Standard, templates
Build
Captain training
Altagether facilitation
Training cohorts
Fair Oaks pilot
Hand-hacked live use case
Pilot in flight
Popup retail
Fair Oaks corridor activation
Activations & community-led commerce
Dashboard MVP
Public accountability layer
Build & launch
Iterate from pilot
Refine
Scale to additional corridors
Roll out
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 8
WHO PAYS
Who pays for what
Sponsors
Pay for their own delivery — out of existing project budgets, not new spend.
EIFD
Funds the engagement infrastructure — administered through the PFA, a small fraction of the $2B financing layer.
Local professionals
Do the work — facilitators, mediators, legal, translators from inside Altadena, so dollars recirculate.
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 9
TEAM & PARTNERS
Team & partners
COLLABORATION TEAM
Altadena Village
Esther Kim
CoLab
Megan Hinchliffe Gerig · Gabriella Caparco
Alting
Petra Wennberg
Altagether
John Mayo · 150+ block captains
SPONSORS
Altadena Bloom
Ty Garrison
Altadena Chamber of Commerce
Judy Matthews
Altadena Collective
Chris Corbett
Altadena Green
Stephanie Landregan · Wynn Wilson
Altadena Heritage
Hans Allhoff · Michele Zack
Altadena Town Council
Dorothy Wong · Morgan Whirledge
ARRC
Anders Corey
CCAR
Hans Allhoff
Dena Hive
Dorothy Wong
League of Women Voters
Joan Riback
Neighbors Building a Greater Altadena
Karen Gibson
NOMA
Steve Lewis
PUSD School Board
Jennifer Hall Lee
Steadfast
Jodi McLaughlin · Hans Allhoff
WRTT
Ty Garrison
ALTADENA VILLAGE · COLAB · ALTING · ALTAGETHER

## Slide 10
WHAT WE WANT FROM YOU TODAY
Endorsement of the approach — co-signing this process.
Not a separate letter to County. Not a budget commitment. CAPS standing alongside Altadena Village, CoLab, Alting, and Altagether in saying this is how community engagement should work. That weight helps move EIFD toward an earmark for the engagement infrastructure.
WHAT ENDORSEMENT ENABLES NEXT
Joint visibility at PFA hearings · your co-signature on the Fair Oaks pilot framing · a credible voice when this lands at ATC